## Slide 1: PERT Chart (Task Dependencies)
Task ID | Task | Duration | Predecessors
1 | Set up Environment | 1 week | -
2 | Implement Signup/Login | 1 week | 1
3 | Signup/Login Testing | 1 week | 2
4 | Design Upload Dataset | 1 week | 2
5 | Dataset Upload Integration | 1 week | 4
6 | Create AuthContext | 1 week | 3
7 | Complete User Profile | 1 week | 3
8 | Initial QA & Bug Fixes | 1 week | 7
9 | Implement Dataset Details | 1 week | 5
10 | Dataset Version Management | 1 week | 9
11 | Create Groups Component | 1 week | 10
12 | Implement Dataset Discussion | 1 week | 11
13 | QA for Dataset Components | 1 week | 12
14 | Dataset Buying Component | 1 week | 13
15 | DUA Component | 1 week | 14
16 | Access Request for Private Dataset | 1 week | 15
17 | Final Testing and QA | 1 week | 16
18 | Final Bug Fixes | 1 week | 17
19 | Soft Launch | 1 week | 18

## Slide 2: Gantt Chart
Chart: 
| Set up Environment | Implement Signup/Login | Signup/Login Testing | Design Upload Dataset | Dataset Upload Integration | Create AuthContext | Complete User Profile | Initial QA & Bug Fixes | Implement Dataset Details | Dataset Version Management | Create Groups Component | Implement Dataset Discussion | QA for Dataset Components | Dataset Buying Component | DUA Component | Access Request for Private Dataset | Final Testing & QA | Final Bug Fixes | Soft Launch
Duration (Weeks) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Slide 3: Task Schedule (Oct - Dec)
Task ID | Task | Oct 1 - 7 | Oct 8 - 14 | Oct 15 - 21 | Oct 22 - 31 | Nov 1 - 7 | Nov 8 - 14 | Nov 15 - 21 | Nov 22 - 30 | Dec 1 - 7 | Dec 8 - 14 | Dec 15 - 21 | Dec 22 - 31
1 | Set up Environment & Basic UI | X |  |  |  |  |  |  |  |  |  |  | 
2 | Implement Signup/Login Components |  | X |  |  |  |  |  |  |  |  |  | 
3 | Signup/Login Integration Testing |  |  | X |  |  |  |  |  |  |  |  | 
4 | Design Upload Dataset Component |  |  |  | X |  |  |  |  |  |  |  | 
5 | Dataset Upload Integration |  |  |  |  | X |  |  |  |  |  |  | 
6 | Create AuthContext |  |  |  | X |  |  |  |  |  |  |  | 
7 | Complete User Profile Component |  |  |  | X |  |  |  |  |  |  |  | 
8 | Initial QA & Bug Fixes |  |  |  |  |  | X |  |  |  |  |  | 
9 | Implement Dataset Details |  |  |  |  |  |  | X |  |  |  |  | 
10 | Dataset Version Management |  |  |  |  |  |  |  | X |  |  |  | 
11 | Create Groups Component |  |  |  |  |  |  |  |  | X |  |  | 
12 | Implement Dataset Discussion |  |  |  |  |  |  |  |  |  | X |  | 
13 | QA for Dataset Components |  |  |  |  |  |  |  |  |  |  | X | 
14 | Dataset Buying Component |  |  |  |  |  |  |  |  |  |  |  | X
15 | DUA Component |  |  |  |  |  |  |  |  |  | X |  | 
16 | Access Request for Private Dataset |  |  |  |  |  |  |  |  |  | X |  | 
17 | Final Testing and QA |  |  |  |  |  |  |  |  |  |  | X | 
18 | Final Bug Fixes |  |  |  |  |  |  |  |  |  |  |  | X
19 | Soft Launch |  |  |  |  |  |  |  |  |  |  |  | X